## Intern Autonomous VAPT Plan and Timeline (May-December 2026)

| Phase | Week | Date | Tasks / Assignment | Risks / Dependencies | Output | Owner / Milestone |
| --- | --- | --- | --- | --- | --- | --- |
| Prepare planning, hand over the VKU office, and introduce projects to interns | - | - 14/05/2026 (to) - 31/05/2026 | - Introduce interns to the projects, tasks to be performed, and working environment - Hand over the working office at VKU to the interns - Prepare planning and the necessary research documents for the 3 projects (VAPT AI, SOC AI, DDC) | The interns are in VKU final exam period, so they cannot research the projects until the end of May | The interns clearly understand the 3 projects and the assigned tasks, and work at the CoE office at VKU | The CoE office key was handed over on 16/05/2026 |
| Read project documents and clearly understand the operating flow | 1 | - 01/06/2026 (to) - 07/06/2026 (For DDC project, #) | - Setup template: Docker base, flag system, logging - Design a separate plugin instance mechanism for each user - Clearly understand the CTFd system # |  | The interns understand the CTFd system, plugins, flags, etc. |  |
|  | 2 | - 08/06/2026 (to) - 14/06/2026 ( For VAPT/SOC AI project ) | - Setup local environment, clone source code - Run the project locally - Configure .env |  | The interns can run the project locally and understand the folder structure |  |
|  | 3 combie# | - 15/06/2026 (to) - 21/06/2026 | - DDC: Deploy CTFd staging, integrate plugins, test challenge/flag flow - VAPT AI: Implement vulnerability analysis/reporting/harness module - SOC AI: Implement alert/log analysis with AI |  | The interns have a demo-ready feature/module for each project |  |
| Research and design solutions | 4 | - 22/06/2026 (to) - 28/06/2026 | - DDC: Deploy dynamic flags for Reverse and Pwn - Create a PCAP file for the reverse challenge type |  | The interns can deploy dynamic flags for Reverse and Pwn challenges and create PCAP files for the challenges |  |
|  | 5 | - 29/06/2026 (to) - 05/07/2026 | - VAPT AI: Research and design optimal solutions for the Harness system, source code, and overall system - SOC AI: Clearly understand Threat Hunting and design Threat Hunting for the SOC AI system |  | The interns can propose optimization directions for VAPT AI and develop suitable Threat Hunting ideas for SOC AI |  |
|  | 6 | - 06/07/2026 (to) - 12/07/2026 | - DDC: Log in to CTFd and deploy the solution directly on the system - VAPT AI: Implement optimized workflow for Harness/source code analysis - SOC AI: Implement Threat Hunting use cases and detection workflow - Create test cases, validate output, fix issues |  | The interns are proficient in working directly on the systems of the 3 projects |  |
| Apply and deploy interns' solutions | 7 | - 13/07/2026 (to) - 19/07/2026 | - DDC: Officially deploy the completed solution to the CTFd system, test the challenge/flag flow, and optimize operations - VAPT AI: Apply the source code/Harness analysis workflow to the project environment, evaluate results, and fine-tune - SOC AI: Deploy Threat Hunting use cases and the detection workflow to the test system |  | The interns can apply the solution to the project environment, test the results, and fine-tune according to each system |  |
| Transition to Autonomous VAPT and SLM research | 8 | 20/07/2026 - 26/07/2026 | Maximize the contextual information obtained from the client, including key details such as the client’s system architecture diagram, website information, frameworks, and technologies used. |  |  | Transition week |
|  | 9 | 27/07/2026 - 31/07/2026 | Reuse reports from previous penetration testing engagements to provide the AI with diverse context from different clients. |  | Approved SLM choice, baseline benchmark, target architecture, and fine-tuning plan. | End-Jul milestone |
| Train the SLM and build the EVVO Harness foundation | 10 | 03/08/2026 - 09/08/2026 | - [Model] Clean, label, and split reports, findings, client questions, remediation text, and false-positive examples into train/validation/test sets. - [Harness] Convert EVVO SOPs, report style, severity logic, validation checks, and answer tone into structured rules and retrieval documents. - [QA] Prepare benchmark questions and gold-standard report-review cases. | Dataset quality, privacy, licensing, hallucination, and training-resource limits. | Dataset v1, EVVO knowledge base v1, and measurable acceptance tests. | Model / Harness / QA |
|  | 11 | 10/08/2026 - 16/08/2026 | - [Model] Run the first adapter/fine-tuning experiment and build the initial retrieval index. - [Harness] Build a report-review pipeline that ingests Leiz output, retrieves EVVO rules, and produces structured review comments. - [QA] Measure accuracy, unsupported claims, latency, and cost against the baseline. |  | SLM v0.1, report-review PoC, and baseline metric report. | Weekly demo |
|  | 12 | 17/08/2026 - 23/08/2026 | - [Model] Improve pentesting knowledge using OSCP-equivalent methodology, vulnerability-validation cases, and hard-negative examples. - [Harness] Add evidence checks, self-validation, consistency review, confidence scoring, and report-based client Q&A. - [QA] Test hallucination, data leakage, weak evidence, and false-positive handling. |  | SLM v0.2, validation workflow, client Q&A beta, and defect list. | Quality gate |
|  | 13 | 24/08/2026 - 30/08/2026 | - [Integration] Connect the SLM and Harness to review outputs and answer client questions using report evidence. - [QA] Compare results with human review, tune thresholds, define escalation rules, and complete regression testing. |  | End-to-end assistant, human-comparison results, and release checklist. | UAT |
|  | 14 | 31/08/2026 | - [All] Demonstrate the trained model and Harness, freeze v1, document gaps, and approve the September backlog. |  | SLM/Harness v1 able to assist report review and answer report-related client questions. | End-Aug milestone |
| Enable direct client interaction with minimal human intervention | 15 | 01/09/2026 - 06/09/2026 | - [Harness] Build authenticated chat/API access, client-specific sessions, conversation memory, and evidence-linked answers. - [All] Define permitted question types, confidence thresholds, escalation conditions, audit logs, and service boundaries. | Tenant isolation, prompt injection, answer accuracy, and escalation reliability. | Client-assistant alpha with controlled access and traceable answers. | Harness + Security |
|  | 16 | 07/09/2026 - 13/09/2026 | - [Harness] Automate report ingestion, retrieval, answer generation, confidence scoring, and low-confidence escalation. - [Model] Tune concise customer-facing responses while preserving EVVO tone and technical accuracy. |  | Minimal-intervention client workflow beta. | Weekly demo |
|  | 17 | 14/09/2026 - 20/09/2026 | - [Security] Implement tenant isolation, RBAC, secrets handling, rate limits, prompt-injection controls, and sensitive-data redaction. - [QA] Test malicious prompts, cross-client leakage, unsupported answers, and audit-log completeness. |  | Security controls and adversarial-test evidence. | Security gate |
|  | 18 | 21/09/2026 - 27/09/2026 | - [All] Run an internal/client-like pilot, monitor accuracy, latency, escalation rate, and unresolved questions, then fix priority defects. - [Harness] Add operational dashboards and feedback capture for continuous improvement. |  | Pilot report, tuned assistant, and operational dashboard. | Pilot |
|  | 19 | 28/09/2026 - 30/09/2026 | - [All] Complete go/no-go review, release the client-interaction workflow, and document remaining human-approval cases. |  | Client-facing assistant v1 operating with minimal human intervention. | End-Sep milestone |
| Build autonomous Web Application VAPT and EVVO report generation | 20 | 01/10/2026 - 04/10/2026 | - [Harness] Define the full Web VAPT workflow: scope/ROE, target discovery, authentication, scanning, evidence collection, validation, and reporting. - [Security] Define scope enforcement, rate limits, safe-stop controls, and prohibited actions. | Authorization, scan safety, tool reliability, false positives, and report-quality equivalence. | Approved Web VAPT architecture, safety gates, and end-to-end test plan. | Architecture |
|  | 21 | 05/10/2026 - 11/10/2026 | - [Harness] Integrate dedicated Nmap, ZAP, Nuclei, and future-scanner sessions with crawling, scan control, and evidence extraction. - [QA] Validate scope restrictions, timeout/retry behavior, and compact tool summaries. |  | Automated Web scanning alpha with traceable tool sessions. | Harness |
|  | 22 | 12/10/2026 - 18/10/2026 | - [Model] Analyze scan evidence, classify findings, reject false positives, request additional evidence, and perform controlled validation. - [Harness] Capture reproducible requests/responses, affected assets, impact, and validation history. |  | Validated-finding pipeline beta with reproducible evidence. | Model + Harness |
|  | 23 | 19/10/2026 - 25/10/2026 | - [Reporting] Generate EVVO-format findings, CVSS/severity, remediation, executive summary, scope, methodology, and evidence references. - [QA] Compare the generated report with the current human-produced report and correct quality gaps. |  | Automated report v0.9 and documented human-comparison score. | Reporting gate |
|  | 24 | 26/10/2026 - 31/10/2026 | - [All] Run a complete authorized assessment against lab/staging targets, resolve critical defects, and complete release documentation. |  | Autonomous Web Application VAPT v1 generating the EVVO report format. | End-Oct milestone |
| Productize and sell the Web VAPT service online | 25 | 01/11/2026 - 08/11/2026 | - [Product/Harness] Define signup, service packages, scope submission, target-ownership verification, legal consent/ROE, and job status. - [Platform] Build tenant, project, scan-job, artifact, and report management. | Payment/compliance, target ownership, multi-tenant isolation, abuse prevention, and production operations. | Commercial product specification and portal/API alpha. | Product |
|  | 26 | 09/11/2026 - 15/11/2026 | - [Platform] Integrate payment-provider sandbox checkout, credit-card payment flow, invoice/receipt, order status, and scan activation after authorization. - [QA] Test failed payment, duplicate order, cancellation, and refund-support paths. |  | Sandbox payment and authorized scan-job creation flow. | Payment |
|  | 27 | 16/11/2026 - 22/11/2026 | - [Platform] Add quotas, scheduling, worker isolation, encrypted artifacts, monitoring, retries, cancellation, notifications, and support logs. - [Security] Review secrets, data retention, tenant boundaries, and administrative access. |  | Production-like staging platform with operational controls. | Operations |
|  | 28 | 23/11/2026 - 29/11/2026 | - [All] Run end-to-end commercial UAT from payment to report delivery, complete security/privacy review, and fix launch blockers. - [Support] Prepare customer guidance, service limitations, and incident/escalation procedures. |  | Release candidate, UAT evidence, and launch checklist. | Commercial UAT |
|  | 29 | 30/11/2026 | - [All] Complete go-live review and release a controlled commercial beta for online Web Application VAPT. |  | Sellable online Web VAPT platform v1. | End-Nov milestone |
| Extend Autonomous VAPT to Network Pentesting | 30 | 01/12/2026 - 06/12/2026 | - [Harness/Security] Define IP ownership verification, network ROE, allowlists, safe scan profiles, credentialed/non-credentialed modes, and stop conditions. - [Model] Define network finding taxonomy, evidence requirements, and attack-path reasoning criteria. | Explicit authorization, intrusive scans, credential handling, network disruption, and scanner coverage. | Network VAPT architecture, safety policy, and acceptance tests. | Architecture |
|  | 31 | 07/12/2026 - 13/12/2026 | - [Harness] Integrate discovery, port/service fingerprinting, vulnerability scanners, credentialed checks, and dedicated tool sessions. - [QA] Normalize scanner evidence and test timeout, retry, scope, and deduplication behavior. |  | Autonomous network-scanning alpha with normalized evidence. | Harness |
|  | 32 | 14/12/2026 - 20/12/2026 | Validate network findings, identify attack paths, assess false positives, calculate severity, and recommend remediation. Generate the EVVO network pentest report with evidence and executive summary. |  | Network VAPT beta and generated report. | Model + Reporting |
|  | 33 | 21/12/2026 - 27/12/2026 | - [All] Run end-to-end tests on authorized lab/staging networks, compare with human pentester results, and tune safety, coverage, performance, and report quality. |  | UAT report, resolved priority defects, and release candidate. | UAT |
|  | 34 | 28/12/2026 - 31/12/2026 | - [All] Complete the final demo, documentation, operating guide, source-code handover, backlog, and production-readiness review. |  | Autonomous Network Pentesting v1 and full handover package. | End-Dec milestone |

| VAPT AI | Detailed VAPT AI Harness Plan | Intern Tasks |
| --- | --- | --- |

This section details the VAPT AI workstream for interns. The main objective is to enhance the Harness system so it can orchestrate AI agents and scanning tools more efficiently, reduce unnecessary AI cost and context usage, validate findings more reliably, and manage each scan tool through a dedicated session until the analysis and exploitation flow is completed.

1.1 AI Cost & Context Optimization

•  Review the current Harness workflow to identify token-heavy steps, duplicated context, repeated model calls, and tool-output bloat.

•  Implement context-reduction logic so the Harness only sends relevant scan evidence, affected assets, concise summaries, and required historical decisions to the AI.

•  Add session summarization and context breakpoints after each major analysis stage to prevent long-session context accumulation.

•  Apply cost-aware orchestration: use lightweight prompts or models for simple validation and reserve stronger reasoning only for complex vulnerability analysis.

•  Track prompt size, response size, tool-output size, number of AI calls, and estimated cost for each workflow run.

•  Expected output: an optimized Harness workflow that reduces unnecessary AI context and operating cost while maintaining vulnerability analysis quality.

1.2 AI Self-Validation & Vulnerability Confirmation

•  Update the Harness so that when the AI finds useful information, it must perform a self-confirmation step before marking the item as a vulnerability.

•  For every potential finding, require the AI to verify the affected asset, source of evidence, exploitation condition, security impact, reproducibility, and false-positive possibility.

•  Force a structured classification decision: Confirmed Vulnerability, Potential Issue, Informational Finding, or False Positive.

•  Require a concise rationale and supporting evidence before the Harness allows the finding to be added to the report.

•  If evidence is insufficient, the Harness must trigger a re-check step, request more scan data, run an additional tool action, or mark the item as pending.

•  Expected output: a more reliable vulnerability-validation flow with reduced false positives and clearer reasoning for each reported issue.

1.3 Tool-Specific Break Sessions for Scanning Workflows (time)

•  Implement break-session logic for each integrated scanning tool, including Nmap, ZAP, Nuclei, and other future scanners.

•  When a scan starts, the Harness must create a dedicated session for that specific tool and follow the session until the tool output is fully processed.

•  For each tool session, the Harness should extract relevant evidence, summarize scan results, ask the AI to analyze the findings, and continue follow-up actions until the exploitation or validation flow is completed.

•  Nmap session: parse open ports, services, versions, scripts, and trigger service-specific follow-up analysis.

•  ZAP session: follow crawling, passive scan, active scan, alert validation, and request/response evidence review.

•  Nuclei session: validate template matches, affected endpoints, severity, matcher evidence, and false-positive risk.

•  Each tool session must output a compact structured summary to the global Harness context instead of pushing raw logs into every later AI call.

•  Expected output: independent per-tool analysis sessions with better traceability, smaller context size, and clearer workflow control.

| SOC AI | Detailed SOC AI Threat Intelligence & Enrichment Plan | Intern Tasks |
| --- | --- | --- |

This section details the SOC AI workstream for interns. The main objective is to develop a stronger threat intelligence and enrichment capability for SOC AI so the system can collect, normalize, validate, score, and attach external threat context to security events before they are used for detection, investigation, threat hunting, or reporting. The focus is not on AI Alert generation, but on building a reliable enrichment layer that improves log context, reduces false positives, and helps analysts understand the reputation, risk, and relevance of suspicious indicators.

2.1 Threat Intelligence Source Collection & Feed Management

•  Review the current SOC AI enrichment workflow, including local malicious IP lists, enrichment scripts, existing log fields, and the current output schema.

•  Identify suitable threat intelligence sources such as AbuseIPDB, AlienVault OTX, MISP, URLhaus, ThreatFox, Spamhaus, internal blocklists, customer allowlists, and any available commercial feeds.

•  Design a feed-management mechanism that supports scheduled collection, source metadata, update frequency, confidence score, first seen, last seen, expiry time, and feed health status.

•  Normalize indicators of compromise into a common structure, including IP addresses, domains, URLs, hashes, ASN, country, threat tags, categories, and confidence values.

•  Implement cache and reload logic so enrichment data can be refreshed without restarting the pipeline and without repeated external lookups for the same indicator.

•  Track feed size, last update time, failed updates, duplicate indicators, expired indicators, and source reliability metrics.

•  Expected output: a maintainable threat-intelligence feed layer that can collect and normalize multiple IOC sources for SOC AI enrichment use cases.

2.2 Event Enrichment Pipeline & Context Tagging

•  Extend the enrichment workflow so it can enrich not only source IP but also destination IP, domain, URL, hostname, file hash, user, asset, and cloud resource identifiers when available.

•  Create a structured enrichment object for each event, including indicator value, indicator type, matched source, confidence score, severity, category, tags, reputation, reason, first seen, last seen, and expiry status.

•  Apply enrichment consistently to normalized and deduplicated logs from AWS WAF, VPC Flow Logs, Windows Events, firewall logs, endpoint logs, and future SOC data sources.

•  Add allowlist and suppression logic for trusted internal systems, customer-approved scanners, known NAT gateways, monitoring tools, and business-critical services to reduce false positives.

•  Handle missing, malformed, private, reserved, or internal IP addresses safely so the enrichment service does not crash or generate misleading threat-intelligence results.

•  Optimize output size by storing only useful enrichment context in the final event and avoiding unnecessary duplication of raw feed data.

•  Expected output: an improved enrichment pipeline that attaches clear, structured, and analyst-friendly threat context to security events before further SOC analysis.

2.3 Threat Intelligence Validation, Scoring & Correlation

•  Define validation logic to avoid treating every IOC match as high risk; each match should be evaluated by source reliability, confidence score, indicator age, expiry status, event direction, asset criticality, and business context.

•  Implement risk-prioritization logic that combines threat intelligence confidence with event context such as blocked or allowed action, sensitive destination port, exposed service, authentication result, and repeated activity count.

•  Correlate repeated matches across multiple events so the system can identify patterns such as one malicious IP targeting many URIs, one host contacting many suspicious destinations, or repeated authentication attempts from a suspicious source.

•  Support multi-source confirmation, where indicators seen in more than one trusted feed receive higher confidence than indicators from a single low-confidence source.

•  Create clear classification labels such as Known Malicious, Suspicious, Low Confidence, Benign/Allowlisted, Expired IOC, and Needs Review.

•  Prepare test cases using sample WAF, VPC, Windows, firewall, and endpoint logs to validate enrichment accuracy, false-positive handling, and scoring consistency.

•  Expected output: a validated threat-intelligence scoring and correlation workflow that helps SOC AI provide stronger context for investigation and threat hunting without focusing on alert generation.

2.4 Documentation, Testing & Handover

•  Document the enrichment architecture, supported IOC types, feed sources, refresh logic, field mapping, output schema, allowlist rules, and known limitations.

•  Create sample input and output files showing how raw security events become enriched events with threat-intelligence context.

•  Build unit tests and small end-to-end test cases for feed parsing, IOC lookup, enrichment output, scoring logic, allowlist handling, and malformed data handling.

•  Prepare operational guidance for updating threat-intelligence feeds, rotating output files, checking service status, troubleshooting failed feed loads, and validating enrichment quality.

•  Expected output: complete technical documentation, test evidence, and handover material so the SOC AI enrichment module can be maintained and extended by the team.